## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Dark
PROJECT: Event Planner Site
Jephta Zekeng | Mohammad Ahmadzai |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Panu Khumchoo-Joonpijarn |  | Kacper Popis
Project start date: | 13/11/2024 |  |  |  |  | December | [20 empty] | January
Scrolling increment: | 2 | time axis 2024-12-12 to 2025-02-05
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
D2 - Database and Web Application design planning document [15%, Group-based] | Milestone | Group | 99% | 2024-11-11 | 33 | bar: T to F
D2 Database Plans/Designs - ERD | Goal | Panu | 99% | 2024-01-12 | 12
D2 Milestone Submission | Milestone | Group | 85% | 2024-12-13 | 1 | bar: F
D2 - Overall Project Planning - Gaant Chart | Low Risk | Panu | 99% | 2024-12-10 | 2
D2 - Web Application Plans/Design - Sitemap | Low Risk | Kacper | 90% | 2024-12-08 | 1
D2 - Web Application Plans/Design - Figma (Customer) | On Track | Kacper, Ali, Jephta | 99% | 2024-12-08 | 7
D2 - Web Application Plans/Design - Figma (Services) | On Track | Kacper, Ali, Jephta | 99% | 2024-12-08 | 7 | bar: S to W
D2 - Document (Web Application Plans/Design - Figma) | On Track | Ali, Jephta | 99% | 2024-01-12 | 7 | S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2
D2 - Document (Web Application Plans/Design - Sitemap) | On Track | Kacper, Jephta | 80% | 2024-01-12 | 5 | S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2
D2 - Document (Project Planning and ERD Design) | On Track | Panu, Ali | 80% | 2024-12-08 | 5
Assignment D3 - ERM and Final Application Submission | Milestone | Group | 0% | 2024-12-14 | 33
D3 - Front End Development | Goal | Kacper, Jephta, Panu | 0% | 2024-12-14 | 33
D3 - Back End Development | Goal | Kacper, Panu, Ali | 0% | 2024-12-14 | 33
D3 - Database using SQL on a host DBMS | On Track | Kacper, Panu, Ali | 0% | 2024-12-14
D3 - Development of Web App Client and Server-side Web scripting | On Track | Kacper, Panu, Jephta | 0% | 2024-12-14
D3 - Application of UI | On Track | Ali, Jephta | 0% | 2024-12-14
TITLE 3
TITLE 4
To add more data, Insert new rows ABOVE this one